UWB Real-Time Location System

Vendor Evaluation & Implementation Roadmap

Pair Eyewear  ·  Lab_Assistant Program  ·  Prepared March 1, 2026

| ±10–30cm Target Accuracy | 120 Tags Tray Fleet Size | 2 Sites Est. Coverage | ~8 Units Anchors Required |
| --- | --- | --- | --- |

# Executive Summary

This document evaluates three leading UWB RTLS vendors for integration with the Pair Eyewear Lab_Assistant manufacturing execution system. The goal is real-time tray tracking across the lens lab floor — giving operators and supervisors instant visibility into where every job is without relying on vendor software that does not meet operational needs.

The recommended implementation approach is a phased strategy: deploy UWB position-reporting tags first (Phase 1) to prove ROI and establish the data infrastructure, then add e-ink display capability in later phases. This de-risks the investment and delivers value from the first month.

# Why UWB Over BLE or Wi-Fi

The Pair Eyewear lens lab environment creates exactly the conditions where BLE RSSI positioning fails:

- Metal equipment — oven enclosures, coating machines, and metal workbenches cause multipath reflection that degrades BLE accuracy to ±3–5 meters

- Dense RF environment — multiple Wi-Fi networks, barcode scanners, and industrial equipment create interference

- Fine-grained zone detection needed — knowing a tray is "in coating" is not enough; you need to know which machine, which rack, which workstation

UWB avoids these problems by design. Its time-of-flight measurement operates in nanoseconds — so short that reflected signals arrive too late to corrupt the measurement. The result is consistent ±10–30cm accuracy in environments that would make BLE tracking unreliable.

# Vendor Comparison

| Criteria | Pozyx | Sewio / HID | Eliko |
| --- | --- | --- | --- |
| Accuracy | 10–30cm | 30cm | 10–30cm |
| API | MQTT + HTTP | Open API (REST) | NMEA + REST |
| Setup Complexity | Low — PoE, auto-detect | Medium | Medium |
| Tag IP Rating | IP66/67 | IP67 | IP67 |
| Tag Battery Life | 5+ years | 5+ years | 3–5 years |
| Two-way Comms | Limited | Partial | Yes — LED/vibrate |
| Custom Firmware | No | Yes (partners) | On request |
| Pilot Kit | Yes — ships fast | Yes | Rental program |
| Best For | Fast deployment | Customization | Developer control |
| Recommendation | ★ Start here | Parallel quote | Skip for now |

# Vendor Profiles

| 🥇 Pozyx RECOMMENDED |  |
| --- | --- |
| Website | pozyx.io · docs: docs.pozyx.io |
| Accuracy | 10–30cm UWB, 5m BLE fallback |
| API | MQTT (live stream) + HTTP REST (config/CRUD) |
| Tag Form Factors | Asset tag (IP66/67), wearable, forklift sensor |
| Anchor Setup | PoE or DC powered, VESA wall/ceiling mount, Ethernet daisy chain (up to 8/chain) |
| Tag Price | ~$40–60/tag (request quote for 120 units) |
| Anchor Price | ~$150–250/anchor |
| Starter Kit | Non-Productive Kit for pilots — includes server, anchors, tags |
| Integration | Subscribe MQTT topic → receive {tag_id, x, y, z, timestamp} per update |
| Standards | Omlox certified — interoperability guaranteed |
| Lab_Assistant | Replace getUWBPos() with MQTT subscription — estimated 1–2 weeks dev |

### Pozyx MQTT Payload Example

{ "tagId": "T-047", "x": 4.23, "y": 8.91, "z": 1.1, "timestamp": 1735700000000, "battery": 87, "moving": true }

This payload maps directly to the Lab_Assistant tray model — tagId matches tray ID, x/y feeds the UWB Position Map, battery drives the fleet battery KPIs. No transformation layer needed.

| 🥈 Sewio / HID Global PARALLEL QUOTE |  |
| --- | --- |
| Website | sewio.net (now under HID Global) |
| Accuracy | 30cm in industrial environments |
| API | Fully documented Open REST API — bidirectional |
| Tag Form Factors | Asset, personnel, vehicle (no battery) |
| Key Advantage | Source code and PCB blueprints available to partners — path to custom hardware |
| Tag Price | ~$50–80/tag (HID pricing — request quote) |
| Anchor Price | ~$200–300/anchor |
| Integration | REST webhooks or polling — slightly more setup than MQTT |
| Lab_Assistant | Webhook endpoint in oven-timer-server.js — estimated 2–3 weeks dev |
| Consider if | You plan to build custom tags in Phase 3 or need firmware access |

| 🥉 Eliko SKIP FOR NOW |  |
| --- | --- |
| Website | eliko.tech |
| Accuracy | 10–30cm (TWR protocol) |
| API | NMEA protocol + REST API |
| Key Feature | Two-way comms: push LED flash or vibrate to specific tags |
| Key Limitation | Smaller vendor, longer support response times, less North America presence |
| Rental Option | Yes — 1 month minimum, good for POC without purchase commitment |
| Consider if | You want the LED confirmation feature on the tag itself (binding confirmation) |
| Verdict | Interesting feature set but Pozyx delivers more for less complexity at your scale |

# Cost Model — 120 Tray Fleet

| Line Item | Unit Cost | Qty | Total (Est.) |
| --- | --- | --- | --- |
| UWB Asset Tags (Pozyx IP67) | $50 | 120 | $6,000 |
| UWB Anchors | $200 | 8 | $1,600 |
| Pozyx Positioning Server | $1,500 | 1 | $1,500 |
| Cables, mounting hardware | — | — | $400 |
| Lab_Assistant Integration Dev | $150/hr | 40 hrs | $6,000 |
| Anchor Installation (IT) | $100/hr | 8 hrs | $800 |
| TOTAL HARDWARE |  |  | $9,500 |
| TOTAL IMPLEMENTATION |  |  | $6,800 |
| TOTAL PROJECT COST |  |  | ~$16,300 |

Note: All costs are estimates. Request formal quotes from Pozyx at pozyx.io/contact. Hardware costs typically drop 15–25% at 100+ unit quantities. Dev hours assume integration by someone familiar with the existing Lab_Assistant codebase.

# Implementation Roadmap

| Phase | Name | Timeline | Description |
| --- | --- | --- | --- |
| Phase 1 | UWB Position Only START HERE | Month 1–2 | Tags + anchors + MQTT API feed to Lab_Assistant. Full floor visibility with no display hardware. |
| Phase 2 | E-Ink Display PLANNED | Month 3–5 | Add e-ink display layer. Job barcode, RX data, and routing pushed to tray display on bind. |
| Phase 3 | UWB + E-Ink Combo ROADMAP | Month 6–9 | Custom PCB combining nRF52840 (BLE) + DW3110 (UWB) + e-paper. ~$45–60/unit at 500+ qty. |
| Phase 4 | AI Integration VISION | Month 10+ | Predictive routing, anomaly alerts, AI-generated shift reports from real position data. |

## Phase 1 Detail — UWB Position Only (Recommended Start)

Phase 1 requires no display hardware, no custom firmware, and no changes to existing lab workflows. Tags are attached to trays and start reporting positions immediately after anchor installation.

### What Gets Built

- MQTT bridge — Node.js subscription to Pozyx MQTT stream, feeding {tray_id, x, y, zone} into Lab_Assistant

- Zone detection — compare x/y coordinates against zone polygons to automatically assign department (Coating, Assembly, QC, etc.)

- Live floor map — UWB Position Map tab already built in Lab_Assistant v2.1 — replace simulated positions with live MQTT data

- Battery monitoring — Pozyx tags report battery level per payload, feeds existing Fleet Overview battery KPIs

- Alerts — tag not seen for >10 minutes triggers notification; rush job in wrong zone triggers Slack alert

### What You Get Immediately

- Real-time position of every tray on the lab floor — no scanning, no manual updates

- Automatic department detection — system knows when a tray enters and exits Coating, Assembly, QC

- Rush job floor visibility — AI assistant can answer "where is job J21694 right now" from live data

- Dwell time analytics — how long does each tray spend in each zone, automatically

- Foundation data for Phase 2 routing intelligence

# Recommended Next Steps

- Contact Pozyx (pozyx.io/contact) — request a quote for 120 tags, 8 anchors, 1 positioning server, and a pilot kit for initial testing

- Request a parallel quote from Sewio/HID for comparison — specifically ask about custom firmware access for Phase 3 planning

- Walk the two Irvine sites with IT — identify ceiling/wall anchor mount points, confirm PoE switch capacity (8 additional ports), map cable runs

- Use the Pozyx anchor planning tool (available in their portal) to model coverage before purchasing — validate 8 anchors is sufficient for your floor plan

- Once vendor selected and kit received, begin MQTT integration — estimated 1–2 weeks to replace simulated UWB data in Lab_Assistant with live Pozyx feed

Document generated by Lab_Assistant AI for internal planning purposes. Vendor pricing is estimated — request formal quotes before budget approval. Technology specifications current as of March 2026.